## Product Backlog
Product Backlog — Enterprise MoU Management System (EMMS)
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate (pts) | Actual Effort (days)
SPRINT 1 ¦ 01 Dec 2025 – 31 Dec 2025 ¦ Foundation & Setup ¦ 10 pts
1 | User Authentication & Login | Authentication | As a faculty member or management user, I want to register and log in securely so that I can access the system with the correct permissions for my role. | Must | Done | 1. Faculty logs in and lands on Faculty Dashboard. 2. Management logs in and lands on Management Dashboard. 3. Unregistered user is redirected to the login page. 4. Wrong credentials show a clear error message. 5. Logout clears session and returns user to login. | Email/password sign-up with role assignment. Role-based redirect after login. Logout clears all session data. All pages blocked without login. | Login completes within 2 seconds. Passwords never stored in plain text. Unauthorised users are blocked and redirected immediately. | 5
2 | Security & Performance Standards | Infrastructure | As a system stakeholder, I want the application to meet baseline security and performance standards so that user data is protected and the system is reliable for everyday use. | Must | Done | 1. Faculty accessing management pages sees Access Denied. 2. All pages load within 2 seconds under normal use. 3. Sensitive credentials not visible in logs. 4. Logged-out users cannot access any protected content. | Every action requires login. Management sections blocked for faculty with Access Denied message. All user inputs validated before saving. Credentials stored securely and never hard-coded. | All core actions complete within 2 seconds. No sensitive data in system logs. Secure connections enforced in production environment. | 5
SPRINT 2 ¦ 01 Jan 2026 – 31 Jan 2026 ¦ Core MoU & Organisation Features ¦ 16 pts
3 | Organisation Management | MoU Management | As a faculty member or management user, I want to manage the list of organisations so that MoUs are linked to correctly identified companies and institutions. | Should | Done | 1. Faculty can add a new organisation and use it in an MoU immediately. 2. Management can edit organisation details; faculty sees read-only view. 3. Creating a duplicate organisation name shows a warning. 4. Organisation detail page shows all linked MoUs. | Organisation profile includes name, industry, contact email, phone, website, and status. Faculty can create; only management can edit or deactivate. Cannot delete an org with linked MoUs — deactivate instead. | Case-insensitive name search. Paginated list for large datasets. Deactivated organisations preserved in system for historical MoU integrity. | 5
4 | MoU Creation Form | MoU Management | As a faculty member, I want to create a new MoU entry so that I can begin tracking collaboration with a company or organisation. | Must | Done | 1. A valid form with all required fields successfully creates an MoU. 2. New MoU appears immediately in the faculty member's MoU list. 3. Missing required fields show clear inline error messages. 4. Organisation dropdown shows all existing organisations. | MoU must have title, organisation, start date, end date, and faculty owner. System auto-sets status to Active. Faculty can create a new organisation inline. System warns on duplicate active MoU for same faculty and organisation. | Form submits within 2 seconds. All input fields sanitised before saving. MoU saved reliably with no silent failures. | 5
5 | View & Filter MoU List | MoU Management | As a faculty member, I want to view and filter my MoUs so that I can quickly find specific agreements and monitor their current statuses. | Must | Done | 1. Faculty sees only their own MoUs in the list. 2. Expiring Soon filter shows only MoUs due within 30 days. 3. Searching an organisation name correctly narrows the list. 4. Clicking an MoU row opens the full detail page. | List shows title, organisation, start/end date, status badge, and days to expiry. Filter options: All, Active, Expiring Soon, Expired, Renewed. Case-insensitive search. Default sort: soonest expiry first. | Search results update within 0.5 seconds. Handles 100+ MoUs without performance issues. Responsive layout on desktop and tablet. | 3
6 | Faculty Dashboard Overview | Faculty | As a faculty member, I want a clear dashboard showing the status of all my MoUs at a glance so that I can quickly identify what needs my attention. | Must | Done | 1. Summary counts match the actual number of MoUs in each status. 2. MoUs with no activity in 90+ days are clearly highlighted. 3. Clicking a summary card navigates to the filtered MoU list. 4. No other faculty member's data appears on the dashboard. | Dashboard shows counts for Total, Active, Expiring Soon, and Expired MoUs. Flags any MoU with no logged activity in 90+ days. Shows the 5 most recent activities across all faculty MoUs. Data scoped strictly to the logged-in user. | Loads within 3 seconds. Data belongs only to the logged-in user — no cross-user data leakage. Clean and uncluttered layout. | 3
SPRINT 3 ¦ 01 Feb 2026 – 28 Feb 2026 ¦ Activity Tracking & Notifications ¦ 13 pts
7 | Log Activity on MoU | Activity Tracking | As a faculty member, I want to log activities against an MoU so that I can maintain a record of collaboration and keep the MoU marked as active in the system. | Must | Done | 1. Logging an activity updates the last interaction date on the MoU. 2. An active grace period is automatically resolved when an activity is logged. 3. The submitted activity appears at the top of the timeline immediately. 4. Once saved, the activity cannot be edited or deleted by anyone. | Activity must include type, date, and description. Logging updates MoU last interaction date. Auto-resolves any active grace period on that MoU. Activities displayed in reverse-chronological order. Activity types: Meeting, Workshop, Internship, Project, Other. | Activity and MoU date update saved together — one must not save without the other. Activity entries are immutable after submission. Handles concurrent submissions without errors. | 5
8 | Expiry Alerts & Notifications | Notifications | As a faculty member, I want to be alerted when an MoU is nearing its expiry so that I can decide whether to renew it or let it expire before the deadline. | Should | Done | 1. An MoU expiring in 20 days shows Expiring Soon with days remaining. 2. An MoU past its end date is shown as Expired in the list. 3. Faculty dashboard shows total count of expiring MoUs. 4. Faculty can dismiss an alert and it disappears for the session. | MoUs within 30 days of end date flagged as Expiring Soon. MoUs past end date auto-set to Expired status. Faculty see their own alerts; management sees all expiring MoUs. Alerts clearly show days remaining to expiry. | Expiry check runs at least once daily. Alerts shown as banners — must not block the user's workflow. All dates stored in consistent UTC format. | 3
9 | Management Dashboard | Management | As a management user, I want to view all MoUs across all faculty members so that I can monitor the overall health of institutional partnerships. | Must | Done | 1. A faculty user trying to access the management dashboard sees Access Denied. 2. Dashboard shows MoUs from all faculty members across the institution. 3. Filtering by faculty name correctly narrows the list. 4. MoUs with an active grace period are clearly highlighted. | Management sees all MoUs regardless of faculty owner. Stats include: total, active, expiring, expired, and stale (90+ days inactive). Filter by faculty name or department. Each MoU row shows the owning faculty member's name. Read-only view — management cannot edit MoUs here. | Faculty users blocked with Access Denied. Dashboard data must not be more than 1 minute out of date. Loads within 3 seconds even with 500+ MoUs in the system. | 5
SPRINT 4 ¦ 01 Mar 2026 – 27 Mar 2026 ¦ Advanced Features & Administration ¦ 42 pts
10 | MoU Edit & Renewal | MoU Lifecycle | As a faculty member, I want to renew an expiring or expired MoU so that the collaboration continues without losing the original agreement's full history. | Should | In Progress | 1. Renewing an expired MoU creates a new MoU linked to the original. 2. The original MoU status changes to Renewed and becomes read-only. 3. The new MoU appears in the faculty member's active MoU list. 4. MoU detail page shows Renewed from [original title] with a clickable link. | Renewal creates a brand new MoU record — original is preserved and marked Renewed. Renewal form pre-fills org, faculty, and description from original (all editable). New MoU carries a reference back to the original. Already-renewed MoUs cannot be renewed again — button is hidden. | Original status update and new MoU creation must succeed or fail together — no partial saves. Full renewal chain preserved no matter how many times renewed. Renewal auto-recorded as an activity on the new MoU. | 8
11 | Inactivity & Grace Period Management | Activity Tracking | As a management user, I want the system to automatically detect MoUs with no activity in 90+ days and flag them so that faculty are prompted to take action. | Must | In Progress | 1. An MoU with 91+ days of no activity appears in the stale MoUs list. 2. A grace period is automatically created for each newly stale MoU. 3. Logging an activity resolves the grace period (status changes to Resolved). 4. Grace period is visible to both the owning faculty and management. | MoU is stale if no activity in 90 days. One grace period created per stale MoU — no duplicates. Grace period includes: linked MoU, creation date, status (Active / Resolved). Faculty see their own; management sees all. Activity logged on MoU auto-resolves its active grace period. | Inactivity check is idempotent — running it multiple times creates no duplicates. Efficient query design for scanning all MoUs. All grace period state changes logged for audit. | 8
12 | Manage Faculty Accounts | Management | As a management user, I want to manage faculty accounts so that I can oversee system access and maintain data integrity when faculty members leave the institution. | Should | In Progress | 1. Management can view all registered faculty with their MoU counts. 2. Deactivating a faculty account immediately prevents them from logging in. 3. Active MoUs of a deactivated faculty can be reassigned to another member. 4. Faculty users attempting to access this section see Access Denied. | View all faculty: name, email, department, MoU count, last login date. Deactivation suspends login access. Management must reassign active MoUs before or during deactivation. Deactivated accounts stay in system as Inactive — never permanently deleted. | Deactivation and MoU reassignment are atomic — both succeed or neither proceeds. Audit log records who deactivated each account and when. Faculty list paginates for departments with 50+ members. | 8
13 | Activity History & Audit Log | Activity Tracking | As a management user, I want to view the complete activity history for any MoU so that I can audit collaboration progress and ensure accurate record-keeping. | Could | To Do | 1. MoU detail page shows all activities in reverse-chronological order. 2. Filtering by activity type correctly narrows the timeline. 3. Management can download the activity log as a CSV file. 4. Attempting to edit or delete an activity returns an error — not permitted. | Activities displayed newest first. Each entry shows type, date, faculty name, and description. Management can filter by date range and activity type. CSV export available for management. No edit or delete operations permitted on activity records. | Timeline paginates at 20 entries per page. CSV export handles up to 1,000 records within 5 seconds. Activity data indexed by MoU and date for fast retrieval. | 5
14 | MoU Document Upload | Document Management | As a faculty member, I want to upload the signed MoU document so that the digital record is linked to the physical agreement for reference and compliance. | Should | To Do | 1. Faculty can upload a PDF under 10MB and see it linked to the MoU. 2. Uploading a non-PDF file shows Only PDF files are accepted. 3. Uploading a file over 10MB shows File size exceeds 10MB limit. 4. Document is viewable and downloadable by the faculty owner and management. | PDF files only accepted (validated on both sides). Maximum file size 10MB. Stored securely and linked to the MoU record. Faculty can replace an existing upload. Document visible to owning faculty and management only. | Files not publicly accessible — authentication required to view or download. Upload progress indicator shown during upload. Secure file handling to prevent malicious uploads. | 5
15 | Analytics & Reporting | Management | As a management user, I want to view analytics and generate reports on MoU activity so that I can present institutional partnership data to leadership and identify trends. | Could | To Do | 1. Analytics page renders all charts with real data from the system. 2. Changing the date range updates all charts and key figures immediately. 3. Export produces a downloadable file with all currently visible data. 4. A faculty user trying to access this page is redirected to their own dashboard. | Charts: MoUs by status (pie), new MoUs per month (line), MoUs by department (bar). KPI cards: total MoUs, average duration, most active faculty, top organisation. Date range filter updates all charts. Export in PDF or CSV format. Management-only access. | All charts and KPIs load within 5 seconds for 1,000+ MoUs. Renders clearly on standard desktop and large monitors. Exported report neatly formatted and suitable for leadership presentation. | 8